## NTINF
(Product) | Backlog |  |  | Natuurkunde en Technologie voor informatici
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
VANDEWAL Koen
Backlog | [8 empty] | Tasks | [12 empty] | Burndown chart date | data |  |  |  | Verbeteringen volgende backlog
Work Date | Work Day | Total Tasks | Tasks Remaining (this day) | Total Tasks Completed (this day) | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Exercise number | Priority (/10) | Title | Description | Datalink (URL) | Received (Date) | Deadline (Date) | Owner | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours)
2020-09-21 | 1 | 3 | 2 | 1 | 1 | 1.5 | 1.5 | 100 | 1 | Chapt 2,3 | 7 | Hoorcollege | Les 1 hoorcollege volgen | Notes: Hoorcollege 1 | 2020-09-21 | / | Maties | 1.5 | 1.5 | 100 | Done | 1.5 | 1.5 |  |  |  | 1. toevoegen van deadline voor taken |  | ✔
[5 empty] | 2 | 4 | 2.5 | 60 | 2 | Chapt 2,3 | 6 | Samenvatten | Les 1 Slides & Boek samenvatten | Notes: Samenvatting 1 | 2020-09-22 | 2020-09-26 | Maties | 4 | 2.5 | 60 | In Progress | 5.5 | 4 |  |  |  | 2. modulair maken zodat je delen kan copy pasten uit andere backlogs |  | Bezig
[9 empty] | 3 | Chapt 2,3 | 9 | Oefeningen | Les 1 Oefeningen studieleidraad maken |  | 2020-09-23 | 2020-09-27 | Maties | 0 | 0 | 0 | Unstarted | 5.5 | 4 |  |  |  | 3. links naar inhoud |  | ✔
[27 empty] | 4. accumulate gebruiken? |  | ?
[27 empty] | 5. proberen schattingen beter te maken |  | Bezig
[27 empty] | 6. date off recieved assignment, date off deadline |  | ✔
[27 empty] | 7. owner status easily addible |  | ✔
[27 empty] | 8. template for other backlogs |  | ✔
9. better data representation
(how long does it generally take to end an assignment)
(how many are currently done, in progress and unstarted)
(average recieved per day, week, month)
(…) -> get creative
10. get used to excel so you can implement scripts & other features into backlog
[27 empty] | 11. better description of what task at hand and their separation |  | Bezig
[27 empty] | 12. automatically updated cells |  | ?
[27 empty] | 13. meer tussenvormen van progression (almost done, just started, halfway, …) |  | Nog doen
Status data
[24 empty] | Done | In Progress | Unstarted
[24 empty] | 1 | 1 | 1

## OGP2
(Product) | Backlog |  |  | Object Georiënteerd Programmeren 2
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [12 empty] | Burndown chart date | data |  | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining (this day) | Total Tasks Completed (this day) | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Datalink (URL) | Received (Date) | Deadline (Date) | Owner | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) |  | Done | In Progress | Unstarted
2020-09-22 | 1 | 3 | 1 | 2 | 1 | 1.5 | 1.5 | 100 | 1 | H1, 2, 3, 4 | 7 | Hoorcollege | Bekijken en notities maken bij hoorcollege. | Notes: Hoorcollege 1 | 2020-09-22 | / | Maties | 1.5 | 1.5 | 100 | Done | 1.5 | 1.5 |  | 2 | 1 | 0
[5 empty] | 2 | 2 | 4 | 100 | 2 | H1, 2, 4 | 8 | Leeswerk | Lees de opgegeven chapters en vat de belangrijke dingen wat al lopend samen | Notes: OGP2 | 2020-09-22 | / | Maties | 2 | 4 | 100 | Done | 3.5 | 5.5
[5 empty] | 3 | 4 | 1 | 10 | 3 | H1, 2, 3, 4 | 9 | Oefeningen | Maak alle oefeningen in eclipse |  | 2020-09-22 | 2020-09-27 | Maties | 4 | 1 | 10 | In Progress | 7.5 | 6.5
Remove the unnecessary tasks from these charts!
Unnecessary task
Redacted, extra, outdaded

## WEBPR
(Product) | Backlog |  |  | WEBPR
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [12 empty] | Burndown chart date | data | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining | Total Tasks Completed | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Datalink (URL) | Received (Date) | Deadline (Date) | Owner | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) | Done | In Progress | Unstarted
2020-09-23 | 1 | 4 | 0 | 4 | 1 | 1.5 | 1.5 | 100 | 1 | Les 1 | 7 | Hoorcollege | Bekijken en notities maken bij hoorcollege. | Notes: Hoorcollege 1 | 2020-09-22 | / | Maties | 1.5 | 1.5 | 100 | Done | 1.5 | 1.5 | 2 | 0 | 0
[5 empty] | 2 | 0.5 | 0.5 | 100 | 2 | Les 1 | 8 | Leeswerk | Word-Wide Web leeswerk en schrijf al lopend een samenvattinkje | Notes: Zelfstudieopdrachten | 2020-09-22 | / | Maties | 0.5 | 0.5 | 100 | Done | 2 | 2
[5 empty] | 3 | 2 | 3 | 100 | 3 | Les 1 | 8 | Oefeningen | Maak alle oefeningen, denkvragen | Notes: Zelfstudieopdrachten, Finder/WEBPR/Exercises | 2020-09-22 | / | Maties | 2 | 3 | 100 | Practically Done | 4 | 5
[5 empty] | 4 | 2 | 2 | 100 | 4 | Les 1 | 9 | Project | Maak al een structuur voor het project | Notes: Project, Finder: /WEBPR/Project | 2020-09-22 | 2020-09-30 | Maties | 2 | 2 | 100 | Practically Done | 6 | 7

## FUNPR
(Product) | Backlog |  |  | Functioneel Programmeren
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [12 empty] | Burndown chart date | data | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining | Total Tasks Completed | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Datalink (URL) | Received (Date) | Deadline (Date) | Owner | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) | Done | In Progress | Unstarted
2020-09-24 | 1 | 3 | 1 | 2 | 1 | 1.5 | 1.5 | 100 | 1 | H1, 2, 3 | 7 | Hoorcollege | Bekijken en notities maken bij hoorcollege. | Notes: Hoorcollege 1 | 2020-09-24 | / | Maties | 1.5 | 1.5 | 100 | Done | 1.5 | 1.5 | 2 | 1 | 0
[5 empty] | 2 | 2 | 2.5 | 100 | 2 | H1, 2, 3 | 8 | Leeswerk | The Little Schemer en beantwoord de vragen | Files: 2eBachelor | 2020-09-24 | / | Maties | 2 | 2.5 | 100 | Done | 3.5 | 4
[5 empty] | 3 | 1 | 2 | 50 | 3 | H1, 2, 3 | 9 | Oefeningen | Maak alle oefeningen in DrRacket | Finder: /FUNPR/Exercises | 2020-09-24 | 2020-09-27 | Maties | 1 | 2 | 50 | In Progress | 4.5 | 6

## A&D
(Product) | Backlog |  |  | Algoritmen & Datastructuren
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [12 empty] | Burndown chart date | data | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining | Total Tasks Completed | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Datalink (URL) | Received (Date) | Deadline (Date) | Owner | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) | Done | In Progress | Unstarted
2020-09-25 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 100 | 1 | Les 1 | 7 | Hoorcollege | Bekijken en notities maken bij hoorcollege. | Notes: Hoorcollege 1 | 2020-09-25 | / | Maties | 2 | 2 | 100 | Done | 2 | 2 | 1 | 1 | 0
[5 empty] | 2 | 1 | 1 | 75 | 2 |  | 8 | Leeswerk | lezen van Inleiding, studieleidraad, correctheid algemeen | Files: /2eBachelor/A&D | 2020-09-25 | 2020-09-27 | Maties | 1 | 1 | 75 | In Progress | 3 | 3
[9 empty] | 3 |  | 9 | Oefeningen | Maak de laatste 2 oefeningen in de handout | Notes: Zelfstudieopdrachten | 2020-09-25 | 2020-09-27 | Maties