## NTINF
(Product) | Backlog |  |  | Natuurkunde en Technologie voor informatici
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
VANDEWAL Koen
Backlog | [8 empty] | Tasks | [12 empty] | Burndown chart date | data |  |  |  | Verbeteringen volgende backlog
Work Date | Work Day | Total Tasks | Tasks Remaining (this day) | Total Tasks Completed (this day) | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Exercise number | Priority (/10) | Title | Description | Datalink (URL) | Received (Date) | Deadline (Date) | Owner | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours)
2020-09-21 | 1 | 3 | 2 | 1 | 1 | 1.5 | 1.5 | 100 | 1 | Chapt 2,3 | 7 | Hoorcollege | Les 1 hoorcollege volgen | Notes: Hoorcollege 1 | 2020-09-21 | / | Maties | 1.5 | 1.5 | 100 | Done | 1.5 | 1.5 |  |  |  | 1. toevoegen van deadline voor taken |  | ✔
[5 empty] | 2 | 4 | 2.5 | 60 | 2 | Chapt 2,3 | 6 | Samenvatten | Les 1 Slides & Boek samenvatten | Notes: Samenvatting 1 | 2020-09-22 | 2020-09-26 | Maties | 4 | 2.5 | 60 | In Progress | 5.5 | 4 |  |  |  | 2. modulair maken zodat je delen kan copy pasten uit andere backlogs |  | Bezig
[9 empty] | 3 | Chapt 2,3 | 9 | Oefeningen | Les 1 Oefeningen studieleidraad maken |  | 2020-09-23 | 2020-09-27 | Maties | 0 | 0 | 0 | Unstarted | 5.5 | 4 |  |  |  | 3. links naar inhoud |  | ✔
[22 empty] | 0 | 0 |  |  |  | 4. accumulate gebruiken? |  | ?
[22 empty] | 0 | 0 |  |  |  | 5. proberen schattingen beter te maken |  | Bezig
[22 empty] | 0 | 0 |  |  |  | 6. date off recieved assignment, date off deadline |  | ✔
[22 empty] | 0 | 0 |  |  |  | 7. owner status easily addible |  | ✔
[22 empty] | 0 | 0 |  |  |  | 8. template for other backlogs |  | ✔
[22 empty] | 0 | 0 |  |  |  | 9. better data representation
[22 empty] | 0 | 0 |  |  |  |  | (how long does it generally take to end an assignment)
[22 empty] | 0 | 0 |  |  |  |  | (how many are currently done, in progress and unstarted)
[22 empty] | 0 | 0 |  |  |  |  | (average recieved per day, week, month)
[22 empty] | 0 | 0 |  |  |  |  | (…) -> get creative
[22 empty] | 0 | 0 |  |  |  | 10. get used to excel so you can implement scripts & other features into backlog
[22 empty] | 0 | 0 |  |  |  | 11. better description of what task at hand and their separation |  | Bezig
[22 empty] | 0 | 0 |  |  |  | 12. automatically updated cells |  | ?
[22 empty] | 0 | 0 |  |  |  | 13. meer tussenvormen van progression (almost done, just started, halfway, …) |  | Nog doen
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0 | Status data
[22 empty] | 0 | 0 | Done | In Progress | Unstarted
[22 empty] | 0 | 0 | 1 | 1 | 1
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0
[22 empty] | 0 | 0

## OOP1
(Product) | Backlog |  |  | Object-georiënteerd Programmeren 1
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [8 empty] | Burndown chart date | data |  | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining (this day) | Total Tasks Completed (this day) | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) |  | Done | In Progress | Unstarted
2020-02-18 | 1 | 2 | 1 | 1 | [1] | 1.5 | 2.5 | 100 | [1] | H1-3 | 5 | Inleiding OOP1 | Library iosstream, de verschillen tussen C en C++ bestuderen, aanvulling | 1.5 | 2.5 | 100 | Done | 223 | 266.5 |  | 34 | 1 | 1
[5 empty] | [2] | 6 | 4 | 80 | [2] | H4 | 7 | Klasses & members | Wennen aan de klasses en de leerstof die hier rond draait (oef) | 6 | 5 | 100 | Done | 221.5 | 264
2020-02-19 | 2 | 3 | 0 | 2 | [2] | 2 | 1 | 100 | [3] | H5 | 7 | Aanvulling 1 | Copy, move, convert constructor oefeningen + extra stuff | 6 | 5 | 100 | Done | 215.5 | 259
[5 empty] | [3] | 6 | 5 | 100 | [4] | H4-H5 | 7 | Samenvatting | maak een samenvatting van beide hoofdstukken | 3.5 | 5 | 100 | Done | 209.5 | 254
2020-02-20 | 3 | 5 | 2 | 0 | [4] | 4 | 0.5 | 10 | [5] | H4-H5 | 8 | Extra OEF (plusjes) | breidt je visie uit en werk met std::vector, std::string en nog standaarden | 4 | 3 | 100 | Done | 206 | 249
2020-02-21 | 4 | 5 | 2 | 0 | [5] | 2 | 0.5 | 10 | [6] | Practicum1 | 9 | Chess | Design & voorbereidende implementatie van chess | 8 | 10 | 100 | Done | 202 | 246
2020-02-22 | 5 | 5 | 2 | 0 | / | / | / | / | [7] | H6 | 8 | Samenvatting | samenvatten van H6 | 1 | 1 | 100 | Done | 194 | 236
2020-02-23 | 6 | 5 | 2 | 0 | [4] | 3.5 | 3 | 70 | [8] | H6 | 6 | Oefeningen | alle oefeningen van H6 maken (incl de plusjes) | 5 | 3 | 100 | Done | 193 | 235
2020-02-24 | 7 | 5 | 2 | 0 | [4] | 2 | 1 | 85 | [9] | H7 | 8 | Oefeningen | Alle oefeningen van H7 maken (incl de plusjes) | 3 | 4 | 100 | Done | 188 | 232
2020-02-25 | 8 | 5 | 1 | 1 | [4] | 1 | 1 | 100 | [10] | H7 | 7 | Samenvatting | Samenvatten van H7 + Lezen | 3 | 2 | 100 | Done | 185 | 228
2020-02-26 | 9 | 5 | 0 | 1 | [5] | 3 | 2.5 | 100 | [11] | Practicum1 | 8 | Bijwerken | Bijschaven van nieuwe structuur en verbeteringen begeleider | 9 | 13.5 | 100 | Done | 182 | 226
2020-02-27 | 10 | 6 | 1 | 0 | [6] | 6.5 | 7.5 | 90 | [12] | Practicum2 | 9 | Werken | Toevoegen van andere pieces | 5 | 7 | 100 | Done | 173 | 212.5
2020-02-28 | 11 | 6 | 1 | 0 | / | / | / | / | [13] | H8 | 7 | Oefeningen | Oefeningen van H8 operatoren maken | 4 | 3 | 100 | Done | 168 | 205.5
2020-02-29 | 12 | 6 | 1 | 0 | / | / | / | / | [14] | H8 | 7 | Samenvatting | Lezen + samenvatting van H8 operatoren maken | 3 | 4 | 100 | Done | 164 | 202.5
2020-03-01 | 13 | 6 | 0 | 1 | [6] | 1.5 | 3.5 | 100 | [15] | Les 6 | 6 | Samenvatting | Ontwerpprincipes samenvatten | 2 | 1 | 100 | Done | 161 | 198.5
2020-03-02 | 14 | 6 | 0 | 0 | / | / | / | / | [16] | GUI 1 | 9 | Oefeningen | in oefenen eerste les GUI | 10 | 11 | 95 | In Progress | 159 | 197.5
2020-03-03 | 15 | 8 | 1 | 1 | [8] | 5 | 3 | 100 | [17] | Herhaling | 4 | Herhaling leerstof | herhaal alle laatst geziene hoofdstukken nog eens | 2 | 3 | 100 | Done | 149 | 186.5
2020-03-04 | 16 | 8 | 0 | 1 | [7] | 1 | 1 | 100 | [18] | GUI 2 | 6 | Samenvatting | Samenvatten leerstof voor deel 2 Qt | 1 | 1 | 50 | Deprecated | 147 | 183.5
2020-03-05 | 17 | 10 | 1 | 1 | [9] | 4 | 3 | 100 | [19] | GUI 2 | 8 | Oefeningen | Oefeningen van Qt deel 2 afwerken | 3 | 4 | 80 | Deprecated | 146 | 182.5
[5 empty] | [10] | 1 | 0.5 | 20 | [20] | GUI 2 | 5 | Extra | Oefeningen voorbereidend werk voor project eens bekijken | 0 | 0 |  | Unstarted | 143 | 178.5
2020-03-06 | 18 | 11 | 2 | 0 | / | / | / | / | [21] | Practicum 3 | 8.5 | First steps | Maken van backlog, schets, eerste stappen | 3 | 3 | 100 | Done | 143 | 178.5
2020-03-07 | 19 | 11 | 2 | 0 | / | / | / | / | [22] | Extra | 6 | Calculator | Maak je eigen calculator in Qt | 6 | 2 | 35 | Deprecated | 140 | 175.5
2020-03-08 | 20 | 11 | 2 | 0 | / | / | / | / | [23] | H9 | 7 | Samenvatting | Aanvullingen 2 samenvatten en lezen | 2 | 3 | 100 | Done | 134 | 173.5
2020-03-09 | 21 | 12 | 3 | 0 | [11] | 4 | 3 | 70 | [24] | H9 | 7 | Oefeningen | Oefeningen van aanvullingen 2 H9 | 4 | 4.5 | 100 | Done | 132 | 170.5
2020-03-10 | 22 | 12 | 3 | 0 | [11] | 3 | 2 | 90 | [25] | Practicum 3 | 8 | Middel | Taakverdeling, UML, Programmeren | 13 | 13.5 | 100 | Done | 128 | 166
2020-03-11 | 23 | 12 | 3 | 0 | / | / | / | / | [26] | Practicum 3 | 8 | Herwerk | Revision van tips van begeleider | 1 | 4 | 100 | Done | 115 | 152.5
2020-03-12 | 24 | 12 | 3 | 0 | [11] | 5 | 5 | 80 | [27] | Practicum 3 | 8.5 | Eventhandling | Zorgen voor cellwidgets, pieceviews & boardwidget | 7 | 7 | 100 | Done | 114 | 148.5
2020-03-13 | 25 | 12 | 3 | 0 | / | / | / | / | [28] | Practicum 3 | 9 | Afwerking | Connecties, QgraphicsView, Model & View, Moves | 7 | 5 | 50 | Deprecated | 107 | 141.5
2020-03-14 | 26 | 12 | 3 | 0 | / | / | / | / | [29] | Project | 8 | Milestone 1 | ULM, Mijlpalen, requirements, schets, git | 18 | 21 | 100 | Done | 100 | 136.5
2020-03-15 | 27 | 12 | 2 | 1 | [11] | 3 | 3 | 100 | [30] | Project | 8.5 | Milestone 2 | afwerken van UML, afwerken van mijlpalen, beginnen bulletrapport, taken | 27 | 26 | 100 | Done | 82 | 115.5
2020-03-16 | 28 | 12 | 2 | 0 | [10] | 1 | 0.5 | 50 | [31] | Project | 7 | Milestone 3 | UML, bulletrapport, save & load, ... | 6 | 6 | 100 | Done | 55 | 89.5
|  |  |  | / | [12] | 3 | 4 | 80 | [32] | Project | 8 | Milestone 4 | Cards teovoegen, properties kopen, gameloop | 17 | 17 | 100 | Done | 49 | 83.5
2020-03-17 | 29 | 15 | 3 | 2 | [10] | 2 | 1 | 100 | [33] | Project | 7.5 | Milestone 5 | Save, load en newgame afwerken. Quality of life. Wat voor werken (nextTurn) | 4 | 6.5 | 100 | Done | 32 | 66.5
|  |  |  | / | [12] | 2 | 4 | 100 | [34] | Project | 8 | Milestone 6 | NextTurn(), kunnen bieden | 7 | 10 | 100 | Done | 28 | 60
|  |  |  | / | [13] | 2 | 1 | 40 | [35] | Project | 6 | Milestone 7 | Overleaf starten, takenverdeling housecleaning, vragen doorsturen | 2 | 2 | 100 | Done | 21 | 50
2020-03-18 | 30 | 15 | 2 | 1 | [13] | 2 | 2 | 100 | [36] | Project | 7 | Milestone 8 | ppt opmaak, verslag maken, cleanup, bugfixen, UML | 3 | 27 | 100 | Done | 19 | 48
|  |  |  | / | [14] | 2 | 1 | 50 | [37] | Project | 9.5 | Powerpoint | Presenteren van demo en powerpoint, vragen beantwoorden | 2 | 2 | 100 | Done | 16 | 21
2020-03-19 | 31 | 15 | 2 | 0 | [16] | 6 | 7 | 80 | [38] | Theorie | 10 | Alle theorie | Hoofdstuk 1-9 nakijken | 5 | 7 | 100 | Done | 14 | 19
2020-03-20 | 32 | 17 | 4 | 0 | [16] | 4 | 4 | 95 | [39] | Theorie | 10 | HC, Cursus & RC | Hoorcolleges, Cursus nalezen & Responsiecolleges | 2 | 2 | 100 | Done | 9 | 12
[5 empty] | [14] | 1 | 2 | 80 | [40] | Praktijk | 10 | Alle oefeningen | Alle oefeningen maken van Hoofdstuk 1-9 | 7 | 10 | 100 | Done | 7 | 10
2020-03-21 | 33 | 17 | 3 | 1 | [14] | 1 | 1 | 100
2020-03-22 | 34 | 17 | 2 | 1 | [15] | 2 | 1 | 100
2020-03-23 | 35 | 17 | 2 | 0 | / | / | / | /
2020-03-24 | 36 | 17 | 2 | 0 | / | / | / | /
2020-03-25 | 37 | 17 | 2 | 0 | / | / | / | /
2020-03-26 | 38 | 20 | 5 | 0 | [18] | 1 | 1 | 50 | [11 empty] | Remove the unnecessary tasks from these charts!
[5 empty] | [19] | 3 | 4 | 80
2020-03-27 | 39 | 20 | 5 | 0 | / | / | / | / | [11 empty] | Unnecessary task
2020-03-28 | 40 | 20 | 5 | 0 | / | / | / | / | [11 empty] | Redacted, extra, outdaded
2020-03-29 | 41 | 20 | 5 | 0 | / | / | / | /
2020-03-30 | 42 | 20 | 5 | 0 | / | / | / | /
2020-03-31 | 43 | 22 | 6 | 1 | [21] | 3 | 3 | 100
[5 empty] | [26] | 2 | 2 | 70
2020-04-01 | 44 | 23 | 7 | 0 | [22] | 2 | 2 | 35
2020-04-02 | 45 | 25 | 8 | 1 | [23] | 2 | 3 | 100
[5 empty] | [24] | 3 | 3.5 | 80
2020-04-03 | 46 | 25 | 8 | 0 | / | / | / | /
2020-04-04 | 47 | 26 | 9 | 0 | [25] | 1 | 0.5 | 10
[5 empty] | [26] | 1 | 1 | 80
2020-04-05 | 48 | 26 | 8 | 1 | [25] | 4 | 4 | 40
[5 empty] | [26] | 1 | 2 | 100
2020-04-06 | 49 | 26 | 7 | 1 | [25] | 7 | 7 | 100
2020-04-07 | 50 | 27 | 7 | 1 | [27] | 7 | 7 | 100
2020-04-08 | 51 | 28 | 8 | 0 | [28] | 7 | 5 | 50
2020-04-09 | 52 | 29 | 9 | 0 | [29] | 7 | 9 | 50
2020-04-10 | 53 | 29 | 9 | 0 | / | / | / | /
2020-04-11 | 54 | 29 | 9 | 0 | [29] | 4.5 | 5 | 70
2020-04-12 | 55 | 29 | 8 | 1 | [29] | 4 | 7 | 100
2020-04-13 | 56 | 29 | 8 | 0 | / | / | / | /
2020-04-14 | 57 | 30 | 9 | 0 | [30] | 5 | 4 | 10
2020-04-15 | 58 | 30 | 9 | 0 | [30] | 1 | 1 | 15
2020-04-16 | 59 | 30 | 9 | 0 | [30] | 4 | 4 | 30
2020-04-17 | 60 | 30 | 9 | 0 | [30] | 2 | 2 | 40
2020-04-18 | 61 | 30 | 9 | 0 | [30] | 4 | 4 | 50
2020-04-19 | 62 | 30 | 8 | 1 | [30] | 11 | 11 | 100
2020-04-20 | 63 | 30 | 8 | 0 | / | / | / | /
2020-04-21 | 64 | 30 | 8 | 0 | / | / | / | /
2020-04-22 | 65 | 31 | 9 | 0 | [31] | 1 | 1 | 20
2020-04-23 | 66 | 31 | 8 | 1 | [31] | 5 | 5 | 100
2020-04-24 | 67 | 31 | 8 | 0 | / | / | / | /
2020-04-25 | 68 | 32 | 9 | 0 | / | / | / | /
2020-04-26 | 69 | 32 | 9 | 0 | / | / | / | /
2020-04-27 | 70 | 32 | 9 | 0 | / | / | / | /
2020-04-28 | 71 | 28 | 4 | 0 | [32] | 5 | 5 | 30
2020-04-29 | 72 | 28 | 4 | 0 | [32] | 5 | 5 | 65
2020-04-30 | 73 | 28 | 3 | 1 | [32] | 7 | 7 | 100
2020-05-01 | 74 | 29 | 4 | 0 | / | / | / | /
2020-05-02 | 75 | 29 | 4 | 0 | / | / | / | /
2020-05-03 | 76 | 29 | 4 | 0 | / | / | / | /
2020-05-04 | 77 | 29 | 4 | 0 | / | / | / | /
2020-05-05 | 78 | 29 | 4 | 0 | / | / | / | /
2020-05-06 | 79 | 29 | 4 | 0 | [33] | 3 | 5.5 | 80
2020-05-07 | 80 | 29 | 3 | 1 | [33] | 1 | 1 | 100
2020-05-08 | 81 | 30 | 4 | 0 | [34] | 2 | 2 | 20
2020-05-09 | 82 | 30 | 4 | 0 | [34] | 1 | 1 | 30
2020-05-10 | 83 | 30 | 4 | 0 | [34] | 2 | 2 | 60
2020-05-11 | 84 | 30 | 3 | 1 | [34] | 2 | 5 | 100
2020-05-12 | 85 | 30 | 3 | 0 | / | / | / | /
2020-05-13 | 86 | 30 | 3 | 0 | / | / | / | /
2020-05-14 | 87 | 30 | 3 | 0 | / | / | / | /
2020-05-15 | 88 | 30 | 3 | 0 | / | / | / | /
2020-05-16 | 89 | 30 | 3 | 0 | / | / | / | /
2020-05-17 | 90 | 31 | 3 | 1 | [35] | 2 | 2 | 100
2020-05-18 | 91 | 32 | 4 | 0 | [36] | 1 | 1 | 30
2020-05-19 | 92 | 32 | 4 | 0 | / | / | / | /
2020-05-20 | 93 | 32 | 4 | 0 | / | / | / | /
2020-05-21 | 94 | 32 | 4 | 0 | [36] | 2 | 2 | 50
2020-05-22 | 95 | 32 | 4 | 0 | [36] | 5 | 5 | 65
2020-05-23 | 96 | 32 | 4 | 0 | [36] | 5 | 7 | 85
2020-05-24 | 97 | 32 | 3 | 1 | [36] | 11 | 13 | 100
2020-05-25 | 98 | 33 | 3 | 1 | [37] | 2 | 2 | 100
2020-05-26 | 99 | 33 | 3 | 0 | / | / | / | /
2020-05-27 | 100 | 33 | 3 | 0 | / | / | / | /
2020-05-28 | 101 | 33 | 3 | 0 | / | / | / | /
2020-05-29 | 102 | 33 | 3 | 0 | / | / | / | /
2020-05-30 | 103 | 33 | 3 | 0 | / | / | / | /
2020-05-31 | 104 | 33 | 3 | 0 | / | / | / | /
2020-06-01 | 105 | 33 | 3 | 0 | / | / | / | /
2020-06-02 | 106 | 33 | 3 | 0 | / | / | / | /
2020-06-03 | 107 | 33 | 3 | 0 | / | / | / | /
2020-06-04 | 108 | 33 | 3 | 0 | / | / | / | /
2020-06-05 | 109 | 33 | 3 | 0 | / | / | / | /
2020-06-06 | 110 | 33 | 3 | 0 | / | / | / | /
2020-06-07 | 111 | 33 | 3 | 0 | / | / | / | /
2020-06-08 | 112 | 33 | 3 | 0 | / | / | / | /
2020-06-09 | 113 | 33 | 6 | 0 | [38] | 3 | 5 | 80
2020-06-10 | 114 | 33 | 5 | 1 | [38] | 2 | 2 | 100
[5 empty] | [40] | 2 | 3 | 50
2020-06-11 | 115 | 33 | 1 | 4 | [39] | 2 | 2 | 100
[5 empty] | [40] | 5 | 7 | 100
[5 empty] | [17] | 2 | 3 | 100
[5 empty] | [24] | 1 | 1 | 100
2020-06-12 | 116 | 33 | 1 | 0 | / | / | / | /
2020-06-13 | 117 | 33 | 1 | 0 | / | / | / | /
2020-06-14 | 118 | 33 | 1 | 0 | / | / | / | /
2020-06-15 | 119 | 33 | 1 | 0 | / | / | / | /
2020-06-16 | 120 | 33 | 1 | 0 | / | / | / | /
2020-06-17 | 121 | 33 | 1 | 0 | / | / | / | /
2020-06-18 | 122 | 33 | 1 | 0 | / | / | / | /
2020-06-19 | 123 | 33 | 1 | 0 | / | / | / | /
2020-06-20 | 124 | 33 | 1 | 0 | / | / | / | /

## BELIN
(Product) | Backlog |  |  | Beleidsinformatica
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [8 empty] | Burndown chart date | data | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining | Total Tasks Completed | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) | Done | In Progress | Unstarted
2020-02-18 | 1 | 2 | 0 | 0 | / | / | / | / | [1] | Les 1-2 | 6 | samenvatten | geziene leerstof samenvatten | 3 | 0 | 0 | Deprecated | 72.5 | 70.8 | 20 | 0 | 0
2020-02-19 | 2 |  | 0 | 0 | / | / | / | / | [2] | H3,4,5,6 | 8 | lezen | BPMN method & style hoofdstukken lezen | 7 | 6 | 100 | Done | 69.5 | 70.8
2020-02-20 | 3 | 2 | 2 | 0 | / | / | / | / | [3] | Les 3 | 8 | voorbereiding | voorbereiden herstellen van smartphone | 1 | 0.5 | 100 | Done | 62.5 | 64.8
2020-02-21 | 4 |  | 2 | 0 | / | / | / | / | [4] | Les 4 | 7 | voorbereiding | voorbereiden voor volgende les | 2 | 2.5 | 100 | Done | 61.5 | 64.3
2020-02-22 | 5 | 2 | 2 | 0 | / | / | / | / | [5] | Les 5 | 5 | werkzitting | oefeningen bpmn maken in werkzitting | 2 | 2 | 100 | Done | 59.5 | 61.8
2020-02-23 | 6 | 2 | 2 | 0 | [2] | 5 | 2 | 60 | [6] | Les 6 | 7 | Hoorcollege | Hoorcollege samengevat en gekeken | 1 | 1.3 | 100 | Done | 57.5 | 59.8
2020-02-24 | 7 | 3 | 3 | 0 | [2] | 5 | 2 | 80 | [7] | Les 6 | 8 | werkzitting | oefeningen drm, dl, dm | 2 | 4 | 100 | Done | 56.5 | 58.5
2020-02-25 | 8 | 3 | 2 | 1 | [3] | 1 | 0.5 | 100 | [8] | Les 6 | 7.5 | extra leerstof | Lecture notes, boek, extra videos | 1 | 2 | 100 | Done | 54.5 | 54.5
2020-02-26 | 9 | 3 | 2 | 0 | / | / | / | / | [9] | Les 7 | 7 | werkzitting | Oefeningen werkzitting 2 | 2 | 2 | 100 | Done | 53.5 | 52.5
2020-02-27 | 10 | 3 | 2 | 0 | / | / | / | / | [10] | Les 8 | 8 | Hoorcollege | Beluister, Schrijf samenvatting | 1 | 2 | 100 | Done | 51.5 | 50.5
2020-02-28 | 11 | 3 | 2 | 0 | / | / | / | / | [11] | Les 8 | 8.5 | werkzitting | Maken van oefening 1 & 2 | 3 | 3 | 100 | Done | 50.5 | 48.5
2020-02-29 | 12 | 3 | 2 | 0 | / | / | / | / | [12] | Les 9 | 8 | werkzitting | Maak oefening 3 & 4 | 3 | 3 | 100 | Done | 47.5 | 45.5
2020-03-01 | 13 | 3 | 2 | 0 | / | / | / | / | [13] | Les 10 | 8.5 | Hoorcollege | Beluister hoorcollege, lees lecture notes | 2 | 2 | 100 | Done | 44.5 | 42.5
2020-03-02 | 14 | 4 | 3 | 0 | [4] | 1 | 0.2 | 20 | [14] | Les 11 | 7 | Hoorcollege | Beluister hoorcollege | 2.5 | 2.5 | 100 | Done | 42.5 | 40.5
2020-03-03 | 15 | 4 | 3 | 0 | [4] | 1 | 1.2 | 70 | [15] | Les 1 | 9 | Studying | Exame theorie studeren | 4 | 4 | 100 | Done | 40 | 38
2020-03-04 | 16 | 4 | 3 | 0 | / | / | / | / | [16] | Les 2 | 9 | Studying | Exame theorie studeren | 4 | 4 | 100 | Done | 36 | 34
2020-03-05 | 17 | 4 | 3 | 0 | / | / | / | / | [17] | Les 3 | 9 | Studying | Exame theorie studeren | 4 | 3 | 100 | Done | 32 | 30
2020-03-06 | 18 | 4 | 2 | 1 | [4] | 1 | 1.3 | 100 | [18] | Les 4-5-6 | 9 | Studying | Exame theorie studeren | 5 | 5 | 100 | Done | 28 | 27
2020-03-07 | 19 | 4 | 2 | 0 | / | / | / | / | [19] | Les 7-8-9 | 9 | Studying | Exame theorie studeren | 9 | 8 | 100 | Done | 23 | 22
2020-03-08 | 20 | 4 | 2 | 0 | / | / | / | / | [20] | Les 10-11 | 9 | Studying | Exame theorie studeren | 4 | 4 | 100 | Done | 14 | 14
2020-03-09 | 21 | 5 | 2 | 0 | [5] | 2 | 2 | 100 | [21] | All | 9 | Excercises | Examen oefeningen maken | 10 | 10 | 100 | Done | 10 | 10
2020-03-10 | 22 | 5 | 2 | 0 | / | / | / | /
2020-03-11 | 23 | 5 | 2 | 0 | / | / | / | /
2020-03-12 | 24 | 5 | 2 | 0 | / | / | / | /
2020-03-13 | 25 | 5 | 2 | 0 | / | / | / | /
2020-03-14 | 26 | 5 | 2 | 0 | / | / | / | /
2020-03-15 | 27 | 5 | 2 | 0 | / | / | / | /
2020-03-16 | 28 | 5 | 2 | 0 | / | / | / | /
2020-03-17 | 29 | 5 | 2 | 0 | / | / | / | /
2020-03-18 | 30 | 5 | 2 | 0 | / | / | / | /
2020-03-19 | 31 | 5 | 2 | 0 | / | / | / | /
2020-03-20 | 32 | 5 | 2 | 0 | / | / | / | /
2020-03-21 | 33 | 5 | 2 | 0 | / | / | / | /
2020-03-22 | 34 | 5 | 2 | 0 | / | / | / | /
2020-03-23 | 35 | 8 | 4 | 1 | [6] | 1 | 1.3 | 100
2020-03-24 | 36 | 8 | 4 | 0 | / | / | / | /
2020-03-25 | 37 | 8 | 4 | 0 | / | / | / | /
2020-03-26 | 38 | 8 | 4 | 0 | / | / | / | /
2020-03-27 | 39 | 8 | 4 | 0 | / | / | / | /
2020-03-28 | 40 | 8 | 4 | 0 | / | / | / | /
2020-03-29 | 41 | 8 | 4 | 0 | / | / | / | /
2020-03-30 | 42 | 9 | 3 | 2 | [7] | 2 | 4 | 100
[5 empty] | [8] | 1 | 2 | 100
[5 empty] | [9] | 1 | 1 | 80
2020-03-31 | 43 | 9 | 3 | 0 | / | / | / | /
2020-04-01 | 44 | 9 | 3 | 0 | / | / | / | /
2020-04-02 | 45 | 9 | 3 | 0 | / | / | / | /
2020-04-03 | 46 | 9 | 3 | 0 | / | / | / | /
2020-04-04 | 47 | 9 | 3 | 0 | / | / | / | /
2020-04-05 | 48 | 9 | 3 | 0 | / | / | / | /
2020-04-06 | 49 | 9 | 3 | 0 | / | / | / | /
2020-04-07 | 50 | 9 | 3 | 0 | / | / | / | /
2020-04-08 | 51 | 9 | 3 | 0 | / | / | / | /
2020-04-09 | 52 | 9 | 3 | 0 | / | / | / | /
2020-04-10 | 53 | 9 | 3 | 0 | / | / | / | /
2020-04-11 | 54 | 9 | 3 | 0 | / | / | / | /
2020-04-12 | 55 | 9 | 3 | 0 | / | / | / | /
2020-04-13 | 56 | 9 | 3 | 0 | / | / | / | /
2020-04-14 | 57 | 9 | 3 | 0 | / | / | / | /
2020-04-15 | 58 | 9 | 3 | 0 | / | / | / | /
2020-04-16 | 59 | 9 | 3 | 0 | / | / | / | /
2020-04-17 | 60 | 9 | 3 | 0 | / | / | / | /
2020-04-18 | 61 | 9 | 3 | 0 | / | / | / | /
2020-04-19 | 62 | 9 | 3 | 0 | / | / | / | /
2020-04-20 | 63 | 9 | 3 | 0 | / | / | / | /
2020-04-21 | 64 | 9 | 3 | 0 | / | / | / | /
2020-04-22 | 65 | 11 | 4 | 1 | [10] | 1 | 2 | 100
[5 empty] | [11] | 2 | 2 | 90
2020-04-23 | 66 | 11 | 4 | 0 | / | / | / | /
2020-04-24 | 67 | 11 | 4 | 0 | / | / | / | /
2020-04-25 | 68 | 11 | 4 | 0 | / | / | / | /
2020-04-26 | 69 | 11 | 4 | 0 | / | / | / | /
2020-04-27 | 70 | 11 | 4 | 0 | / | / | / | /
2020-04-28 | 71 | 11 | 4 | 0 | / | / | / | /
2020-04-29 | 72 | 11 | 4 | 0 | / | / | / | /
2020-04-30 | 73 | 11 | 4 | 0 | / | / | / | /
2020-05-01 | 74 | 11 | 4 | 0 | / | / | / | /
2020-05-02 | 75 | 11 | 4 | 0 | / | / | / | /
2020-05-03 | 76 | 11 | 4 | 0 | / | / | / | /
2020-05-04 | 77 | 13 | 4 | 2 | [11] | 1 | 1 | 100
[5 empty] | [12] | 3 | 3 | 100
2020-05-05 | 78 | 13 | 4 | 0 | / | / | / | /
2020-05-06 | 79 | 13 | 4 | 0 | / | / | / | /
2020-05-07 | 80 | 13 | 4 | 0 | / | / | / | /
2020-05-08 | 81 | 13 | 4 | 0 | / | / | / | /
2020-05-09 | 82 | 13 | 4 | 0 | / | / | / | /
2020-05-10 | 83 | 13 | 4 | 0 | / | / | / | /
2020-05-11 | 84 | 13 | 4 | 0 | / | / | / | /
2020-05-12 | 85 | 13 | 4 | 0 | / | / | / | /
2020-05-13 | 86 | 13 | 4 | 0 | / | / | / | /
2020-05-14 | 87 | 13 | 4 | 0 | / | / | / | /
2020-05-15 | 88 | 13 | 4 | 0 | / | / | / | /
2020-05-16 | 89 | 13 | 4 | 0 | / | / | / | /
2020-05-17 | 90 | 13 | 4 | 0 | / | / | / | /
2020-05-18 | 91 | 14 | 4 | 0 | [14] | 2.5 | 2.5 | 100
2020-05-19 | 92 | 14 | 4 | 0 | / | / | / | /
2020-05-20 | 93 | 14 | 4 | 0 | / | / | / | /
2020-05-21 | 94 | 14 | 4 | 0 | / | / | / | /
2020-05-22 | 95 | 14 | 4 | 0 | / | / | / | /
2020-05-23 | 96 | 14 | 4 | 0 | / | / | / | /
2020-05-24 | 97 | 14 | 4 | 0 | / | / | / | /
2020-05-25 | 98 | 14 | 4 | 0 | / | / | / | /
2020-05-26 | 99 | 14 | 4 | 0 | / | / | / | /
2020-05-27 | 100 | 14 | 4 | 0 | / | / | / | /
2020-05-28 | 101 | 14 | 4 | 0 | / | / | / | /
2020-05-29 | 102 | 13 | 4 | 0 | / | / | / | /
2020-05-30 | 103 | 15 | 4 | 1 | [15] | 4 | 4 | 100
2020-05-31 | 104 | 16 | 4 | 1 | [16] | 4 | 4 | 100
[5 empty] | [17] | 2 | 1 | 15
2020-06-01 | 105 | 16 | 4 | 0 | / | / | / | /
2020-06-02 | 106 | 16 | 4 | 0 | / | / | / | /
2020-06-03 | 107 | 16 | 4 | 0 | / | / | / | /
2020-06-04 | 108 | 16 | 4 | 0 | / | / | / | /
2020-06-05 | 109 | 16 | 4 | 0 | / | / | / | /
2020-06-06 | 110 | 16 | 4 | 0 | / | / | / | /
2020-06-07 | 111 | 16 | 4 | 0 | / | / | / | /
2020-06-08 | 112 | 16 | 4 | 0 | / | / | / | /
2020-06-09 | 113 | 16 | 4 | 0 | / | / | / | /
2020-06-10 | 114 | 16 | 4 | 0 | / | / | / | /
2020-06-11 | 115 | 16 | 4 | 0 | / | / | / | /
2020-06-12 | 116 | 16 | 4 | 0 | / | / | / | /
2020-06-13 | 117 | 19 | 6 | 1 | [17] | 2 | 2 | 100
2020-06-14 | 118 | 19 | 5 | 1 | [18] | 5 | 4 | 100
2020-06-15 | 119 | 19 | 4 | 2 | [19] | 9 | 8 | 100
[5 empty] | [20] | 4 | 4 | 100
2020-06-16 | 120 | 20 | 2 | 2 | [9] | 1 | 1 | 100
[5 empty] | [13] | 2 | 2 | 100
[5 empty] | [21] | 5 | 5 | 50
2020-06-17 | 121 | 20 | 0 | 2 | [21] | 5 | 5 | 100
[5 empty] | [1] | 2 | 2 | 100
2020-06-18 | 122 | 20 | 0 | 0 | / | / | / | /
2020-06-19 | 1 | 20 | 0 | 0 | / | / | / | /
2020-06-20 | 123 | 20 | 0 | 0 | / | / | / | /

## DATA
(Product) | Backlog |  |  | Databases
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [8 empty] | Burndown chart date | data | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining | Total Tasks Completed | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) | Done | In Progress | Unstarted
2020-02-18 | 1 | 2 | 1 | 0 | / | / | / | / | [1] | Les 1 | 5 | SQL intro | eerste oefeningen met SFW | 3 | 4 | 100 | Done | 125.5 | 132 | 33 | 0 | 0
2020-02-19 | 2 | 3 | 2 | 0 | / | / | / | / | [2] | Les 2 | 6.5 | SQL aanvulling 1 | verdere uitbreiding van SFW | 4 | 5 | 100 | Done | 122.5 | 128
2020-02-20 | 3 | 3 | 2 | 0 | [2] | 4 | 3 | 80 | [3] | Les 1-2 | 7 | samenvatten | werking SQL + extra SFW | 4 | 6 | 100 | Done | 118.5 | 123
2020-02-21 | 4 | 3 | 2 | 0 | / | / | / | / | [4] | Les 3 | 7.5 | oefeningen | eerste aantal oefeningen gemaakt van Les 3 | 5 | 6 | 80 | Deprecated | 114.5 | 117
2020-02-22 | 5 | 3 | 2 | 0 | / | / | / | / | [5] | Les 3 | 7 | nakijken | herbekijk de oefeningen en het boek | 2 | 2 | 50 | Deprecated | 109.5 | 111
2020-02-23 | 6 | 3 | 2 | 0 | / | / | / | / | [6] | Les 3 | 8 | samenvatten | constraints, keys, … | 3 | 3 | 70 | Deprecated | 107.5 | 109
2020-02-24 | 7 | 3 | 2 | 0 | / | / | / | / | [7] | Les 4 | 6 | oefeningen | oefeningen afwerken les 4 | 4 | 4 | 80 | Deprecated | 104.5 | 106
2020-02-25 | 8 | 3 | 2 | 0 | / | / | / | / | [8] | Les 4 | 8 | samenvatten | samenvatten oefeningen les 4 | 0 | 0 | 0 | Deprecated | 100.5 | 102
2020-02-26 | 9 | 6 | 5 | 0 | [4] | 5 | 3 | 60 | [9] | Project 1 | 9 | oefeningen | 8 oefeningen maken en zip uploaden | 10 | 8 | 100 | Done | 100.5 | 102
2020-02-27 | 10 | 6 | 5 | 0 | / | / | / | / | [10] | Les 5 | 6 | Herhaling | Herhalings oefeningen afwerken | 2 | 2 | 80 | Deprecated | 90.5 | 94
2020-02-28 | 11 | 6 | 5 | 0 | / | / | / | / | [11] | Les 7 | 8.5 | Oefeningen | Oefeningen van les 7 (ERD) | 6.5 | 6.5 | 100 | Done | 88.5 | 92
2020-02-29 | 12 | 6 | 5 | 0 | [3] | 2 | 2 | 50 | [12] | Les 7 | 8 | samenvatten | Cursus van deze les samenvatten | 4.5 | 4.5 | 95 | Deprecated | 82 | 85.5
2020-03-01 | 13 | 6 | 4 | 1 | [2] | 2 | 2 | 100 | [13] | Les 3 | 8 | samenvatten | Les 3 samenvatten |  |  | 0 | Deprecated | 77.5 | 81
[5 empty] | [3] | 2 | 2 | 50 | [14] | Project 2 | 9 | oefeningen | Maak deel 1 en deel 2 van ER-diagrammen | 8 | 10 | 90 | Done | 77.5 | 81
2020-03-02 | 14 | 6 | 3 | 1 | [3] | 2 | 2 | 100 | [15] | Les 9 | 8 | Hoorcollege | Luisteren en samenvatten | 3 | 3 | 100 | Done | 69.5 | 71
2020-03-03 | 15 | 6 | 3 | 0 | / | / | / | / | [16] | Les 9 | 8.5 | oefeningen | Maak de oefening + luister responsiecollege | 5 | 5 | 100 | Done | 66.5 | 68
2020-03-04 | 16 | 6 | 3 | 0 | [4] | 2 | 3 | 80 | [17] | Les 10 | 9 | Hoorcollege | Luisteren en samenvatten | 2 | 2.5 | 100 | Done | 61.5 | 63
[5 empty] | [6] | 3 | 3 | 70 | [18] | Les 10 | 9 | oefeningen | Maak de oefeningen | 3 | 3 | 100 | Done | 59.5 | 60.5
2020-03-05 | 17 | 6 | 3 | 0 | / | / | / | / | [19] | Les 11 | 9 | Hoorcollege | Luisteren en samenvatten | 2 | 2.5 | 100 | Done | 56.5 | 57.5
2020-03-06 | 18 | 6 | 3 | 0 | / | / | / | / | [20] | Les 11 | 9 | oefeningen | Maak de oefeningen | 3 | 3 | 100 | Done | 54.5 | 55
2020-03-07 | 19 | 6 | 3 | 0 | / | / | / | / | [21] | Project | 9.5 | Normaalvormen & RD | Maak project | 8 | 5 | 100 | Done | 51.5 | 52
2020-03-08 | 20 | 6 | 3 | 0 | / | / | / | / | [22] | Les 11,10,9 | 8 | Responsiecolleges | Beluisteren, samenvatten, vragen stellen | 0 | 0 |  | Deprecated | 43.5 | 47
2020-03-09 | 21 | 6 | 3 | 0 | / | / | / | / | [9 empty] | 43.5 | 47
2020-03-10 | 22 | 6 | 3 | 0 | / | / | / | / | [23] | Les 1 | 10 | Samenvatting |  | 3 | 3 | 100 | Done | 43.5 | 47
2020-03-11 | 23 | 9 | 6 | 0 | [7] | 4 | 4 | 80 | [24] | Les 1 | 10 | Oefeningen |  | 2 | 2 | 100 | Done | 40.5 | 44
|  | 9 | 6 |  | [10] | 2 | 2 | 80 | [25] | Les 2 | 10 | Samenvatting |  | 3 | 3 | 100 | Done | 38.5 | 42
2020-03-12 | 24 | 9 | 6 | 0 | / | / | / | / | [26] | Les 2 | 10 | Oefeningen |  | 2 | 2 | 100 | Done | 35.5 | 39
2020-03-13 | 25 | 9 | 6 | 0 | / | / | / | / | [27] | Les 3 | 10 | Samenvatting |  | 3 | 3 | 100 | Done | 33.5 | 37
2020-03-14 | 26 | 9 | 6 | 0 | / | / | / | / | [28] | Les 3 | 10 | Oefeningen |  | 2 | 2 | 100 | Done | 30.5 | 34
2020-03-15 | 27 | 9 | 6 | 0 | / | / | / | / | [29] | Les 4 | 9 | Herhaling |  | 1 | 1 | 100 | Done | 28.5 | 32
2020-03-16 | 28 | 9 | 6 | 0 | / | / | / | / | [30] | Les 5 | 10 | Samenvatting |  | 3 | 3 | 100 | Done | 27.5 | 31
2020-03-17 | 29 | 9 | 6 | 0 | / | / | / | / | [31] | Les 5 | 10 | Oefeningen |  | 2 | 2 | 100 | Done | 24.5 | 28
2020-03-18 | 30 | 10 | 7 | 0 | [9] | 6 | 1.5 | 20 | [32] | Les 7 | 10 | Samenvatting |  | 2 | 2 | 100 | Done | 22.5 | 26
2020-03-19 | 31 | 10 | 7 | 0 | / | / | / | / | [33] | Les 7 | 10 | Oefeningen |  | 1 | 1 | 100 | Done | 20.5 | 24
2020-03-20 | 32 | 10 | 7 | 0 | / | / | / | / | [34] | Les 9 | 10 | Samenvatting |  | 2 | 2 | 100 | Done | 19.5 | 23
2020-03-21 | 33 | 10 | 7 | 0 | [9] | 6 | 4 | 80 | [35] | Les 9 | 10 | Oefeningen |  | 1 | 2 | 100 | Done | 17.5 | 21
2020-03-22 | 34 | 10 | 7 | 0 | / | / | / | / | [36] | Les 10 | 10 | Samenvatting |  | 1 | 1 | 100 | Done | 16.5 | 19
2020-03-23 | 35 | 10 | 6 | 1 | [9] | 10 | 8 | 100 | [37] | Les 10 | 10 | Oefeningen |  | 2 | 2 | 100 | Done | 15.5 | 18
2020-03-24 | 36 | 10 | 6 | 0 | / | / | / | / | [38] | Les 11 | 10 | Samenvatting |  | 1 | 1 | 100 | Done | 13.5 | 16
2020-03-25 | 37 | 12 | 8 | 0 | [10] | 3 | 3 | 70 | [39] | Les 11 | 10 | Oefeningen |  | 2 | 2 | 100 | Done | 12.5 | 15
[5 empty] | [11] | 2 | 2 | 70 | [40] | Les 12 | 10 | Samenvatting |  | 1 | 1 | 100 | Done | 10.5 | 13
2020-03-26 | 38 | 12 | 8 | 0 | / | / | / | / | [41] | Les 12 | 10 | Oefeningen |  | 0.5 | 0.5 | 100 | Done | 9.5 | 12
2020-03-27 | 39 | 12 | 8 | 0 | / | / | / | / | [42] | Alles | 10 | HERHAAL ALLES |  | 9 | 11.5 | 100 | Done | 9 | 11.5
2020-03-28 | 40 | 12 | 8 | 0 | / | / | / | /
2020-03-29 | 41 | 13 | 9 | 0 | [5] | 2 | 2 | 50
2020-03-30 | 42 | 13 | 9 | 0 | / | / | / | /
2020-03-31 | 43 | 13 | 9 | 0 | / | / | / | /
2020-04-01 | 44 | 14 | 10 | 0 | [14] | 2 | 1 | 10
2020-04-02 | 45 | 14 | 10 | 0 | / | / | / | /
2020-04-03 | 46 | 14 | 10 | 0 | / | / | / | /
2020-04-04 | 47 | 14 | 10 | 0 | / | / | / | /
2020-04-05 | 48 | 14 | 10 | 0 | / | / | / | /
2020-04-06 | 49 | 14 | 10 | 0 | / | / | / | /
2020-04-07 | 50 | 14 | 10 | 0 | / | / | / | /
2020-04-08 | 51 | 14 | 10 | 0 | / | / | / | /
2020-04-09 | 52 | 14 | 10 | 0 | / | / | / | /
2020-04-10 | 53 | 14 | 10 | 0 | / | / | / | /
2020-04-11 | 54 | 14 | 10 | 0 | / | / | / | /
2020-04-12 | 55 | 14 | 10 | 0 | / | / | / | /
2020-04-13 | 56 | 14 | 10 | 0 | / | / | / | /
2020-04-14 | 57 | 14 | 10 | 0 | / | / | / | /
2020-04-15 | 58 | 14 | 10 | 0 | / | / | / | /
2020-04-16 | 59 | 14 | 10 | 0 | / | / | / | /
2020-04-17 | 60 | 14 | 10 | 0 | / | / | / | /
2020-04-18 | 61 | 14 | 10 | 0 | / | / | / | /
2020-04-19 | 62 | 14 | 10 | 0 | / | / | / | /
2020-04-20 | 63 | 14 | 10 | 0 | / | / | / | /
2020-04-21 | 64 | 14 | 10 | 0 | / | / | / | /
2020-04-22 | 65 | 16 | 12 | 0 | / | / | / | /
2020-04-23 | 66 | 16 | 12 | 0 | / | / | / | /
2020-04-24 | 67 | 16 | 12 | 0 | / | / | / | /
2020-04-25 | 68 | 16 | 12 | 0 | [11] | 1.5 | 1.5 | 90
[5 empty] | [12] | 1.5 | 1.5 | 90
2020-04-26 | 69 | 16 | 11 | 1 | [11] | 2 | 2 | 100
[5 empty] | [12] | 1 | 1 | 95
[5 empty] | [14] | 2 | 2 | 40
2020-04-27 | 70 | 16 | 11 | 0 | [14] | 4 | 7 | 90
2020-04-28 | 71 | 16 | 10 | 1 | [14] | 2 | 2 | 100
[5 empty] | [15] | 1 | 1 | 45
2020-04-29 | 72 | 18 | 12 | 0 | / | / | / | /
2020-04-30 | 73 | 18 | 12 | 0 | / | / | / | /
2020-05-01 | 74 | 18 | 12 | 0 | / | / | / | /
2020-05-02 | 75 | 18 | 11 | 1 | [15] | 2 | 2 | 100
2020-05-03 | 76 | 18 | 11 | 0 | [16] | 3 | 3 | 60
2020-05-04 | 77 | 18 | 11 | 0 | / | / | / | /
2020-05-05 | 78 | 18 | 11 | 0 | / | / | / | /
2020-05-06 | 79 | 18 | 11 | 1 | [16] | 2 | 2 | 100
2020-05-07 | 80 | 18 | 10 | 0 | / | / | / | /
2020-05-08 | 81 | 18 | 10 | 0 | / | / | / | /
2020-05-09 | 82 | 18 | 10 | 0 | / | / | / | /
2020-05-10 | 83 | 18 | 10 | 0 | / | / | / | /
2020-05-11 | 84 | 18 | 10 | 0 | / | / | / | /
2020-05-12 | 85 | 18 | 9 | 1 | [17] | 2 | 2.5 | 100
2020-05-13 | 86 | 20 | 10 | 1 | [18] | 3 | 3 | 100
2020-05-14 | 87 | 20 | 9 | 1 | [19] | 2 | 2.5 | 100
2020-05-15 | 88 | 20 | 9 | 0 | / | / | / | /
2020-05-16 | 89 | 20 | 9 | 0 | / | / | / | /
2020-05-17 | 90 | 22 | 10 | 1 | [20] | 3 | 3 | 100
2020-05-18 | 91 | 22 | 10 | 0 | / | / | / | /
2020-05-19 | 92 | 22 | 10 | 0 | / | / | / | /
2020-05-20 | 93 | 22 | 9 | 1 | 21] | 8 | 5 | 100
2020-05-21 | 94 | 22 | 9 | 0 | / | / | / | /
2020-05-22 | 95 | 22 | 9 | 0 | / | / | / | /
2020-05-23 | 96 | 22 | 9 | 0 | / | / | / | /
2020-05-24 | 97 | 22 | 9 | 0 | / | / | / | /
2020-05-25 | 98 | 22 | 9 | 0 | / | / | / | /
2020-05-26 | 99 | 22 | 9 | 0 | / | / | / | /
2020-05-27 | 100 | 22 | 9 | 0 | / | / | / | /
2020-05-28 | 101 | 22 | 9 | 0 | / | / | / | /
2020-05-29 | 102 | 22 | 9 | 0 | / | / | / | /
2020-05-30 | 103 | 22 | 9 | 0 | / | / | / | /
2020-05-31 | 104 | 22 | 9 | 0 | / | / | / | /
2020-06-01 | 105 | 22 | 9 | 0 | / | / | / | /
2020-06-02 | 106 | 22 | 9 | 0 | / | / | / | /
2020-06-03 | 107 | 17 | 0 | 4 | [23] | 3 | 3 | 100
[5 empty] | [24] | 2 | 2 | 100
[5 empty] | [25] | 3 | 3 | 100
[5 empty] | [26] | 2 | 2 | 100
2020-06-04 | 108 | 22 | 0 | 5 | [27] | 3 | 3 | 100
[5 empty] | [28] | 2 | 2 | 100
[5 empty] | [29] | 1 | 1 | 100
[5 empty] | [30] | 3 | 3 | 100
[5 empty] | [31] | 2 | 2 | 100
2020-06-05 | 109 | 28 | 0 | 6 | [32] | 2 | 2 | 100
[5 empty] | [33] | 1 | 1 | 100
[5 empty] | [34] | 2 | 2 | 100
[5 empty] | [35] | 1 | 2 | 100
[5 empty] | [36] | 1 | 1 | 100
[5 empty] | [37] | 2 | 2 | 100
2020-06-06 | 110 | 33 | 0 | 5 | [38] | 1 | 1 | 100
[5 empty] | [39] | 2 | 2 | 100
[5 empty] | [40] | 1 | 1 | 100
[5 empty] | [41] | 0.5 | 0.5 | 100
[5 empty] | [42] | 9 | 11.5 | 100
2020-06-07 | 111 | 33 | 0 | 0 | / | / | / | /
2020-06-08 | 112 | 33 | 0 | 0 | / | / | / | /
2020-06-09 | 113 | 33 | 0 | 0 | / | / | / | /
2020-06-10 | 114 | 33 | 0 | 0 | / | / | / | /
2020-06-11 | 115 | 33 | 0 | 0 | / | / | / | /
2020-06-12 | 116 | 33 | 0 | 0 | / | / | / | /
2020-06-13 | 117 | 33 | 0 | 0 | / | / | / | /
2020-06-14 | 118 | 33 | 0 | 0 | / | / | / | /
2020-06-15 | 119 | 33 | 0 | 0 | / | / | / | /
2020-06-16 | 120 | 33 | 0 | 0 | / | / | / | /
2020-06-17 | 121 | 33 | 0 | 0 | / | / | / | /
2020-06-18 | 122 | 33 | 0 | 0 | / | / | / | /
2020-06-19 | 123 | 33 | 0 | 0 | / | / | / | /
2020-06-20 | 124 | 33 | 0 | 0 | / | / | / | /

## WISK
(Product) | Backlog |  |  | Object-georiënteerd Programmeren 1
Maties | Claesen |  | 1952678 |  |  |  | maties.claesen@student.uhasselt.be
Backlog | [8 empty] | Tasks | [8 empty] | Burndown chart date | data | Status data
Work Date | Work Day | Total Tasks | Tasks Remaining | Total Tasks Completed | Task numbers | Estimation (hours) | Actual (hours) | Status (%) | Number Task | Chapter/ exercises | Priority (/10) | Title | Description | Estimation (hours) | Actual (hours) | Status (%) | Status | Accumulated Estimated (hours) | Accumulated Actual (hours) | Done | In Progress | Unstarted
2020-02-18 | 1 | 0 | 0 | 0 | / | / | / | / | [1] | Les 1 | 6 | Afwerken | Afwerken van oefeningen van Les 1 | 5 | 6 | 100 | Done | 90 | 95 | 22 | 3 | 0
2020-02-19 | 2 | 0 | 0 | 0 | / | / | / | / | [2] | Les 1 | 7 | Dictaten samenvatten | Samenvatten van dictaten en cursus van eerste les | 4 | 2 | 100 | Done | 85 | 89
2020-02-20 | 3 | 0 | 0 | 0 | / | / | / | / | [3] | Les 2 | 8 | Afwerken | Afwerken van oefeningen van Les 2 | 3 | 4 | 100 | Done | 81 | 87
2020-02-21 | 4 | 2 | 2 | 0 | [1] | 5 | 4 | 80 | [4] | Les 2 | 7 | Samenvatten | Samenvatten van dictaten en cursus van tweede les | 1 | 1 | 100 | Done | 78 | 83
2020-02-22 | 5 | 2 | 2 | 0 | / | / | / | / | [5] | Les 3 | 8 | Afwerken | Afwerken van oefeningen van Les 3 | 3 | 3.5 | 100 | Done | 77 | 82
2020-02-23 | 6 | 2 | 2 | 0 | / | / | / | / | [6] | Les 3 | 7 | Samenvatten | Samenvatten van dictaten en cursus van derde les | 1 | 1 | 50 | In progress | 74 | 78.5
2020-02-24 | 7 | 2 | 2 | 0 | / | / | / | / | [7] | Les 4 | 8 | Afwerken | Afwerken van oefeningen van Les 4 | 6 | 6 | 100 | Done | 73 | 77.5
2020-02-25 | 8 | 2 | 2 | 0 | / | / | / | / | [8] | Les 4 | 7 | Samenvatten | Samenvatten van dictaten en cursus van vierde les | 1 | 1 | 50 | In progress | 67 | 71.5
2020-02-26 | 9 | 2 | 2 | 0 | / | / | / | / | [9] | Les 5 | 8 | Samenvatten | Les bekijken en neerschrijven | 1 | 2 | 100 | Done | 66 | 70.5
2020-02-27 | 10 | 2 | 2 | 0 | / | / | / | / | [10] | Les 5 | 9 | Opdrachten | maak opdrachten a en b (bereken k) | 5 | 8 | 100 | Done | 65 | 68.5
2020-02-28 | 11 | 4 | 4 | 0 | / | / | / | / | [11] | Les 6 | 7 | Samenvatten | Samenvatten van hoorcollege | 2 | 3 | 100 | Done | 60 | 60.5
2020-02-29 | 12 | 4 | 4 | 0 | / | / | / | / | [12] | Les 6 | 8 | Oefeningen | Oefeningen & dictaten bekijken van deze les | 8 | 5 | 85 | Done | 58 | 57.5
2020-03-01 | 13 | 4 | 4 | 0 | / | / | / | / | [13] | Les 7 | 7 | Hoorcollege | Beluisteren & samenvatten | 2 | 3 | 100 | Done | 50 | 52.5
2020-03-02 | 14 | 4 | 4 | 0 | / | / | / | / | [14] | Les 7 | 9 | Opdrachten | Maak opdracht, python simulatie (1D, 1 massa, veer) | 4 | 4 | 100 | Done | 48 | 49.5
2020-03-03 | 15 | 4 | 4 | 0 | / | / | / | / | [15] | Les 8 | 7 | Hoorcollege | Beluisteren & samenvatten | 2 | 2 | 100 | Done | 44 | 45.5
2020-03-04 | 16 | 4 | 4 | 0 | / | / | / | / | [16] | Les 8 | 8 | Opdrachten | maak opdrachten en lees dictaat | 4 | 4 | 70 | In progress | 42 | 43.5
2020-03-05 | 17 | 4 | 4 | 0 | / | / | / | / | [17] | Les 9 | 7 | Hoorcollege | Beluisteren & samenvatten van online hoorcollege | 2 | 2 | 100 | Done | 38 | 39.5
2020-03-06 | 18 | 6 | 6 | 0 | [5] | 3 | 3 | 50 | [18] | Les 9 | 9 | Opdrachten | maak opdracht, python simulatie (2D, ketting van massa’s) | 9 | 9 | 100 | Done | 36 | 37.5
2020-03-07 | 19 | 6 | 6 | 0 | / | / | / | / | [19] | Les 10 | 8 | Hoorcollege | Beluisteren & samenvatten van online hoorcollege | 2 | 2 | 100 | Done | 27 | 28.5
2020-03-08 | 20 | 6 | 3 | 3 | [1] | 2 | 2 | 100 | [20] | Les 10 | 9 | Opdrachten | oefeningen & dictaten bekijken van deze les | 6 | 6 | 100 | Done | 25 | 26.5
[5 empty] | [3] | 2 | 3 | 70 | [21] | Les 11 | 8 | Opdrachten | maak opdracht, touw met demping in veer en lucht | 7 | 8.5 | 100 | Done | 19 | 20.5
[5 empty] | [2] | 4 | 2 | 100 | [22] | Les 11 | 8 | Hoorcollege | Beluisteren & samenvatten van online hoorcollege | 2 | 2 | 100 | Done | 12 | 12
[5 empty] | [4] | 1 | 1 | 100 | [23] | Les 12 | 9 | Opdrachten | Oefeningen & dictaten bekijken van deze les | 4 | 4 | 100 | Done | 10 | 10
2020-03-09 | 21 | 6 | 3 | 0 | / | / | / | / | [24] | Les 12 | 7 | Hoorcollege | Beluisteren & samenvatten van online hoorcollege | 1 | 1 | 100 | Done | 6 | 6
2020-03-10 | 22 | 6 | 3 | 0 | / | / | / | / | [25] | Les 11 | 9 | Oefeningen | Oefeningen & dictaten bekijken van deze les | 5 | 5 | 100 | Done | 5 | 5
2020-03-11 | 23 | 6 | 3 | 0 | / | / | / | /
2020-03-12 | 24 | 6 | 3 | 0 | / | / | / | /
2020-03-13 | 25 | 8 | 3 | 0 | [7] | 4 | 3 | 50
2020-03-14 | 26 | 8 | 3 | 0 | / | / | / | /
2020-03-15 | 27 | 8 | 4 | 1 | [3] | 1 | 1 | 100
2020-03-16 | 28 | 8 | 4 | 0 | / | / | / | /
2020-03-17 | 29 | 8 | 4 | 0 | / | / | / | /
2020-03-18 | 30 | 8 | 4 | 0 | / | / | / | /
2020-03-19 | 31 | 8 | 4 | 0 | / | / | / | /
2020-03-20 | 32 | 10 | 5 | 1 | [9] | 1 | 2 | 100
[5 empty] | [10] | 4 | 0.1 | 10
2020-03-21 | 33 | 10 | 5 | 0 | / | / | / | /
2020-03-22 | 34 | 10 | 5 | 0 | / | / | / | /
2020-03-23 | 35 | 10 | 5 | 0 | / | / | / | /
2020-03-24 | 36 | 10 | 5 | 0 | / | / | / | /
2020-03-25 | 37 | 10 | 5 | 0 | / | / | / | /
2020-03-26 | 38 | 10 | 5 | 0 | / | / | / | /
2020-03-27 | 39 | 12 | 6 | 0 | [11] | 2 | 3 | 100
2020-03-28 | 40 | 12 | 6 | 0 | [10] | 4 | 6 | 90
2020-03-29 | 41 | 12 | 5 | 1 | [10] | 1 | 2 | 100
2020-03-30 | 42 | 12 | 5 | 0 | / | / | / | /
2020-03-31 | 43 | 12 | 5 | 0 | / | / | / | /
2020-04-01 | 44 | 12 | 5 | 0 | / | / | / | /
2020-04-02 | 45 | 12 | 5 | 0 | / | / | / | /
2020-04-03 | 46 | 14 | 6 | 1 | [13] | 2 | 3 | 100
[5 empty] | [14] | 1 | 1 | 10
2020-04-04 | 47 | 14 | 5 | 1 | [5] | 4 | 3 | 100
2020-04-05 | 48 | 14 | 4 | 1 | [6] | 1 | 1 | 50
[5 empty] | [7] | 3 | 3 | 100
[5 empty] | [8] | 1 | 1 | 50
2020-04-06 | 49 | 14 | 4 | 0 | / | / | / | /
2020-04-07 | 50 | 14 | 4 | 0 | / | / | / | /
2020-04-08 | 51 | 14 | 4 | 0 | / | / | / | /
2020-04-09 | 52 | 14 | 4 | 0 | / | / | / | /
2020-04-10 | 53 | 16 | 6 | 0 | / | / | / | /
2020-04-11 | 54 | 16 | 6 | 0 | / | / | / | /
2020-04-12 | 55 | 16 | 6 | 0 | / | / | / | /
2020-04-13 | 56 | 16 | 5 | 1 | [12] | 8 | 5 | 85
2020-04-14 | 57 | 16 | 5 | 0 | / | / | / | /
2020-04-15 | 58 | 16 | 4 | 1 | [15] | 2 | 2 | 100
[5 empty] | [16] | 2 | 2 | 45
2020-04-16 | 59 | 16 | 4 | 0 | / | / | / | /
2020-04-17 | 60 | 16 | 4 | 0 | [14] | 1 | 1 | 40
2020-04-18 | 61 | 16 | 4 | 0 | [14] | 2 | 2 | 90
2020-04-19 | 62 | 16 | 3 | 1 | [14] | 1 | 1 | 100
2020-04-20 | 63 | 16 | 3 | 0 | / | / | / | /
2020-04-21 | 64 | 16 | 3 | 0 | / | / | / | /
2020-04-22 | 65 | 16 | 3 | 0 | / | / | / | /
2020-04-23 | 66 | 16 | 3 | 0 | / | / | / | /
2020-04-24 | 67 | 18 | 3 | 2 | [17] | 2 | 2 | 100
2020-04-25 | 68 | 18 | 3 | 0 | [18] | 1 | 1 | 20
2020-04-26 | 69 | 18 | 3 | 0 | / | / | / | /
2020-04-27 | 70 | 18 | 3 | 0 | / | / | / | /
2020-04-28 | 71 | 18 | 3 | 0 | / | / | / | /
2020-04-29 | 72 | 18 | 3 | 0 | / | / | / | /
2020-04-30 | 73 | 18 | 3 | 0 | / | / | / | /
2020-05-01 | 74 | 18 | 3 | 0 | / | / | / | /
2020-05-02 | 75 | 18 | 3 | 0 | / | / | / | /
2020-05-03 | 76 | 18 | 3 | 0 | / | / | / | /
2020-05-04 | 77 | 18 | 3 | 0 | / | / | / | /
2020-05-05 | 78 | 18 | 3 | 0 | / | / | / | /
2020-05-06 | 79 | 18 | 3 | 0 | / | / | / | /
2020-05-07 | 80 | 18 | 3 | 0 | / | / | / | /
2020-05-08 | 81 | 18 | 3 | 0 | / | / | / | /
2020-05-09 | 82 | 18 | 3 | 0 | [18] | 3 | 7 | 70
2020-05-10 | 83 | 18 | 2 | 1 | [18] | 1 | 1 | 100
2020-05-11 | 84 | 18 | 2 | 0 | / | / | / | /
2020-05-12 | 85 | 18 | 2 | 0 | / | / | / | /
2020-05-13 | 86 | 18 | 2 | 0 | / | / | / | /
2020-05-14 | 87 | 18 | 2 | 0 | / | / | / | /
2020-05-15 | 88 | 19 | 3 | 0 | [21] | 2 | 2.5 | 40
2020-05-16 | 89 | 19 | 3 | 0 | [21] | 3 | 4 | 90
2020-05-17 | 90 | 19 | 3 | 0 | / | / | / | /
2020-05-18 | 91 | 19 | 3 | 0 | / | / | / | /
2020-05-19 | 92 | 19 | 3 | 0 | [16] | 2 | 2 | 70
2020-05-20 | 93 | 19 | 3 | 0 | / | / | / | /
2020-05-21 | 94 | 19 | 3 | 0 | / | / | / | /
2020-05-22 | 95 | 19 | 3 | 0 | / | / | / | /
2020-05-23 | 96 | 19 | 3 | 0 | / | / | / | /
2020-05-24 | 97 | 19 | 3 | 0 | / | / | / | /
2020-05-25 | 98 | 19 | 3 | 0 | / | / | / | /
2020-05-26 | 99 | 21 | 4 | 1 | [16] | 0.5 | 0.5 | 75
[5 empty] | [21] | 2 | 2 | 100
2020-05-27 | 100 | 21 | 4 | 1 | [19] | 2 | 2 | 100
[5 empty] | [20] | 5 | 5 | 70
2020-05-28 | 101 | 21 | 4 | 0 | / | / | / | /
2020-05-29 | 102 | 24 | 6 | 1 | [22] | 2 | 2 | 100
[5 empty] | [25] | 4 | 4 | 80
2020-05-30 | 103 | 24 | 6 | 0 | / | / | / | /
2020-05-31 | 104 | 24 | 6 | 0 | / | / | / | /
2020-06-01 | 105 | 24 | 6 | 0 | / | / | / | /
2020-06-02 | 106 | 25 | 3 | 3 | [24] | 1 | 1 | 100
[5 empty] | [20] | 1 | 1 | 100
[5 empty] | [25] | 1 | 1 | 100
2020-06-03 | 107 | 25 | 3 | 0 | / | / | / | /
2020-06-04 | 108 | 25 | 3 | 0 | / | / | / | /
2020-06-05 | 109 | 25 | 3 | 0 | / | / | / | /
2020-06-06 | 110 | 25 | 3 | 0 | / | / | / | /
2020-06-07 | 111 | 25 | 3 | 0 | / | / | / | /
2020-06-08 | 112 | 25 | 3 | 0 | / | / | / | /
2020-06-09 | 113 | 25 | 3 | 0 | / | / | / | /
2020-06-10 | 114 | 25 | 3 | 0 | / | / | / | /
2020-06-11 | 115 | 25 | 3 | 0 | / | / | / | /
2020-06-12 | 116 | 25 | 3 | 0 | / | / | / | /
2020-06-13 | 117 | 25 | 3 | 0 | / | / | / | /
2020-06-14 | 118 | 25 | 3 | 0 | / | / | / | /
2020-06-15 | 119 | 25 | 3 | 0 | / | / | / | /
2020-06-16 | 120 | 25 | 3 | 0 | / | / | / | /
2020-06-17 | 121 | 25 | 3 | 0 | / | / | / | /
2020-06-18 | 122 | 25 | 3 | 0 | / | / | / | /